ENTERPRISE CONTEXT BRAIN

2-Person POC Execution Plan — Ramu + Reena

Start-to-End Hackathon Delivery Plan | Version 1.0 | August 2026

| Item | Decision |
| --- | --- |
| POC | Enterprise Context Brain |
| Goal | Build a working agentic manager-assistant MVP |
| Team | Ramu + Reena |
| Primary demo | Manager asks why a project is delayed, what changed, current risks, and what action to take |
| MVP sources | Jira-like issues, Git activity, project documents/ADRs |
| Core output | Evidence-backed project briefing + risk analysis + recommended action |
| Action layer | One controlled MCP/tool action with human approval |

# 1. Objective

Build a complete, small version of Enterprise Context Brain: ingest enterprise information → normalize it → store organizational memory → retrieve context → reason with agents → show evidence → request approval → execute one controlled action → record the outcome.

The hackathon priority is a working end-to-end demo, not a full enterprise platform.

# 2. MVP Scope

| Area | Build | Do Not Build Yet |
| --- | --- | --- |
| Data | 3 sources: tickets, Git, documents/ADRs | 10+ connectors |
| Memory | Project, Decision, Risk, Event, Evidence | Full knowledge graph |
| Retrieval | Structured + vector/hybrid | Advanced graph reasoning |
| Agents | Manager + Project/Risk/Decision capabilities | Large autonomous swarm |
| MCP | 1 read + 1 write tool | Enterprise tool marketplace |
| UI | Chat + project health + evidence | Full enterprise portal |
| Security | Basic project/user access checks | Full IAM integration |
| Approval | One human approval flow | Complex approval engine |
| Evaluation | 30–50 benchmark questions | Production evaluation platform |

# 3. Team Responsibilities

## Ramu — AI / Backend / Agent & Context Lead

Own backend architecture, API contracts and integration.

Design PostgreSQL/pgvector memory schema and canonical entities.

Build hybrid retrieval and Context Intelligence Layer.

Build Manager, Project, Risk and Decision agent workflow.

Implement MCP server/tool integration and approval logic.

Implement evidence, confidence, audit trace and backend tests.

Own end-to-end backend integration.

## Reena — Data / UI / Evaluation & Integration Lead

Prepare realistic demo data for tickets, Git, documents, decisions and risks.

Build/maintain ingestion and data-validation scripts.

Build manager chat and project-health UI.

Display evidence, source, timestamp, confidence and risks.

Build approval UI.

Create 30–50 evaluation questions and expected evidence.

Test retrieval quality, UX and demo scenarios.

Prepare screenshots, demo assets and presentation support.

Shared: architecture decisions, daily integration, testing, demo rehearsal and final submission.

# 4. Target Architecture

Manager → React UI → FastAPI → Manager Agent / Orchestrator

→ Context Intelligence: intent + entity + permissions + hybrid retrieval + freshness + authority + context assembly

→ Organizational Memory: PostgreSQL + pgvector + source documents

→ Specialist agents: Project / Risk / Decision

→ MCP Tool Gateway: controlled read/write tools

→ Audit / Agent Trace / Outcome → Memory

# 5. Minimum Data Model

| Entity | Minimum Fields |
| --- | --- |
| Project | id, name, owner, status, health, updated_at |
| Issue | id, project_id, title, status, priority, owner, updated_at |
| Decision | id, project_id, decision, reason, alternatives, owner, date, source_id |
| Risk | id, project_id, description, probability, impact, mitigation, owner, status |
| Event | id, project_id, event_type, description, occurred_at, source_id |
| Evidence | id, source_type, source_id, title, url/path, timestamp, authority, content |

Keep the schema small. These entities are enough to prove the concept.

# 6. Start-to-End Build Plan

## Phase 0 — Alignment & Setup

Owner: Both | Timeline: Day 1

Freeze one demo project and three source types.

Create Git repository, branch strategy, README and task board.

Agree API contracts and database schema.

Create .env.example and local run instructions.

Finalize architecture diagram and demo question.

## Phase 1 — Data & Ingestion

Owner: Reena lead / Ramu support | Timeline: Days 1–2

Create 20–50 tickets, 10–20 Git events and 10–15 project documents/ADRs.

Attach project_id, source_id, timestamp, owner and authority.

Build CSV/JSON/document loaders.

Validate duplicates, missing fields and relationships.

Create one command to load the complete dataset.

## Phase 2 — Memory Store

Owner: Ramu lead | Timeline: Days 2–3

Create PostgreSQL tables.

Enable pgvector and indexes.

Generate embeddings for searchable content.

Store canonical entities separately from raw source text.

Create memory CRUD and seed/load APIs.

## Phase 3 — Context Engine

Owner: Ramu | Timeline: Days 3–4

Implement semantic retrieval.

Add SQL filters for project/status/date.

Add hybrid ranking.

Add freshness and source-authority scores.

Return a context packet where every item contains provenance.

## Phase 4 — Agent Layer

Owner: Ramu | Timeline: Days 4–6

Build Project Agent.

Build Risk Agent.

Build Decision Agent.

Build Manager Agent/orchestrator.

Implement the primary manager question workflow.

Return answer + evidence + confidence + recommended actions.

## Phase 5 — UI

Owner: Reena | Timeline: Days 4–6

Build chat screen.

Build project-health summary.

Show top risks and decisions.

Show evidence cards with source and timestamp.

Add approval dialog.

Add error/loading states.

## Phase 6 — MCP Action

Owner: Ramu lead / Reena test | Timeline: Days 6–7

Create MCP server.

Expose one safe read tool.

Expose one controlled write tool such as create escalation/ticket.

Validate tool inputs and permissions.

Require approval before write.

Record action ID and result.

## Phase 7 — Evaluation & Hardening

Owner: Reena lead / Ramu support | Timeline: Days 7–8

Create 30–50 benchmark questions.

Record expected answers and required evidence.

Test stale and conflicting data.

Test unauthorized project access.

Test approval and rejection.

Measure accuracy, evidence coverage and latency.

## Phase 8 — Integration & Demo

Owner: Both | Timeline: Days 8–9

Connect UI → API → agents → memory → MCP.

Run the demo from a clean startup.

Fix integration issues.

Add logging and error handling.

Create data-reset script and fallback demo.

## Phase 9 — Final Submission

Owner: Both | Timeline: Day 10

Prepare 5–7 minute demo.

Prepare 5-slide pitch.

Prepare business problem, innovation and ROI.

Prepare architecture explanation.

Rehearse twice and freeze the build.

# 7. Ramu Detailed Checklist

| Task | How | Done When |
| --- | --- | --- |
| Backend | FastAPI routes, config, logging, health endpoint | API runs |
| Database | PostgreSQL + pgvector + indexes | Seed data query works |
| Context API | Question/project → ranked context | Relevant evidence returned |
| Hybrid retrieval | Vector + SQL + ranking | Benchmark retrieval passes |
| Memory service | CRUD for decisions/risks/events/evidence | Agents can read/write |
| Agents | Manager → specialist agents → response | Main question works |
| MCP | Explicit schemas + validation + permissions | Read/write tools work |
| Approval | Pending action → user approval → execution | No unapproved write |
| Observability | Request/retrieval/agent/tool logs | Trace available |

# 8. Reena Detailed Checklist

| Task | How | Done When |
| --- | --- | --- |
| Dataset | Prepare realistic project records | All demo questions have data |
| Metadata | Source, timestamp, authority, project, owner | Every fact has provenance |
| Ingestion | CSV/JSON/document loaders | One-command load |
| UI | Chat + project overview | Manager can ask questions |
| Evidence UI | Source, timestamp, confidence | Claims are traceable |
| Risk UI | Probability/impact ranking | Top risks visible |
| Decision UI | Decision/reason/alternatives/outcome | Decision memory is clear |
| Approval UI | Proposed action + Approve/Reject | Manager controls write |
| Evaluation | Gold questions + scoring | Quality report exists |
| Demo assets | Screenshots, slides, backup | Presentation ready |

# 9. Primary Demo Workflow

Manager opens Enterprise Context Brain.

Manager asks: “Why is Project X delayed, what changed this week, and what should I do?”

Manager Agent identifies project and intent.

Context Engine retrieves current issues, Git changes, decisions, risks, events and evidence.

System applies access, freshness and source-authority checks.

Project/Risk/Decision agents analyze the context.

Manager Agent produces a concise briefing with evidence and confidence.

System recommends an action.

Manager reviews the proposed action and approves/rejects it.

MCP executes the approved action.

System records the action, result and outcome in the audit trail/memory.

# 10. Backend Response Contract

| Field | Purpose |
| --- | --- |
| answer | Manager-friendly summary |
| project_status | Current health |
| key_changes | Recent important changes |
| risks | Ranked current risks |
| decisions | Relevant decisions/reasons |
| evidence | Supporting source records |
| confidence | Confidence score |
| recommended_actions | Suggested next steps |
| requires_approval | Approval flag |
| trace_id | Audit/debug reference |

# 11. MCP Plan

Use MCP only for the controlled tool/action layer. Keep organizational memory and context retrieval in the application. MCP tools should have explicit schemas, permissions and validation.

| Tool | Type | Purpose |
| --- | --- | --- |
| get_project_status | Read | Return project status |
| get_open_risks | Read | Return unresolved risks |
| create_escalation | Write | Create escalation/ticket after approval |

The current MCP specification supports tool discovery and structured tool schemas, and its guidance emphasizes user visibility and human control over tool invocation. citeturn0search0turn0search1

This separation also matches enterprise agent architecture patterns where agents coordinate models, tools, knowledge and memory. citeturn0search4

# 12. What NOT to Build

Full enterprise knowledge graph.

10+ enterprise connectors.

Large autonomous agent swarm.

Unrestricted production actions.

Complex approval engine.

Heavy UI animations.

Production-grade IAM integration for the hackathon.

Hidden chain-of-thought display; show concise reasoning summaries and evidence instead.

# 13. Definition of Done

| Area | Done Criteria |
| --- | --- |
| Data | Three sources loaded and linked to one project |
| Memory | Decisions, risks, events and evidence searchable |
| Context | Relevant, permission-filtered context returned |
| Agents | Manager workflow completes end-to-end |
| Evidence | Important claims show source and timestamp |
| MCP | One read and one write tool work |
| Approval | Write action cannot execute without approval |
| UI | Question → answer → evidence → approval works |
| Evaluation | Benchmark and score documented |
| Demo | Clean startup reproduces complete flow |

# 14. Daily Team Plan

| Day | Ramu | Reena | Joint Checkpoint |
| --- | --- | --- | --- |
| 1 | Architecture, API, schema | Dataset, ingestion design, UI wireframe | Freeze MVP |
| 2 | DB + memory | Ingestion + validation | First data load |
| 3 | Retrieval/context | UI + evidence | Question → evidence |
| 4 | Agents | Project/risk UI | First agent demo |
| 5 | Agent orchestration | Decision/evidence UI | Main question works |
| 6 | MCP + approval backend | Approval UI | Action workflow |
| 7 | Hardening | Evaluation benchmark | Quality review |
| 8 | Integration | Evaluation + demo assets | Full demo |
| 9 | Bug fixes | Slides/screenshots | Rehearsal |
| 10 | Final deployment | Final pitch/demo | Submission |

# 15. Repository Structure

enterprise-context-brain/

├── backend/app/{api,agents,context,memory,models,retrieval,mcp,services}

├── backend/tests/

├── frontend/src/{components,pages,services}

├── data/{jira,git,documents}

├── evaluation/

├── docs/

├── docker-compose.yml

└── README.md

# 16. Evaluation Questions

What is the current status of Project X?

Why is Project X delayed?

What changed in the last 7 days?

What are the top three risks?

Who owns the highest-risk item?

Why was the current architecture selected?

What alternatives were considered?

Have we experienced a similar issue before?

What action should the manager take next?

Can the agent create an escalation after manager approval?

# 17. Final Hackathon Demo Script

30 sec — Explain fragmented enterprise context.

45 sec — Introduce Enterprise Context Brain and architecture.

90 sec — Run the main manager question.

60 sec — Drill into a decision and its evidence.

60 sec — Show risk analysis.

60 sec — Demonstrate MCP action + human approval.

30 sec — Show audit/trace and governance.

30 sec — Close with ROI and future roadmap.

# 18. Success Criteria

Clearly demonstrate more than simple RAG.

Use structured organizational context and memory.

Explain decisions using evidence.

Use at least one specialist agent.

Invoke an external tool through MCP.

Require human approval for a meaningful write action.

Show provenance and confidence.

Demonstrate a reusable architecture that can scale to more projects and systems.

# 19. Final Ownership

| Ramu | Reena |
| --- | --- |
| Backend architecture | Demo data |
| Database + memory | Ingestion |
| Context/retrieval | Frontend/UI |
| Agent orchestration | Evidence visualization |
| MCP + approval logic | Evaluation |
| API/integration testing | Demo assets |
| Observability | Presentation support |

Both are jointly responsible for end-to-end integration and final demo stability.